## Test Plan
TEST PLAN – SAP MM & SD Functional Testing ¦ Eluru Priyanka ¦ QA Portfolio
1. Document Information
Document Title | SAP MM & SD Functional Testing – Test Plan
Project | SAP ECC Upgrade & Regression Testing – Coromandel International Limited
Version | v1.0
Prepared By | Eluru Priyanka – Associate IT Analyst (QA)
Date | March 2023
Review Status | Approved
2. Scope of Testing
In Scope | SAP MM: Purchase Requisition, Purchase Order, Goods Receipt, Invoice Verification (LIV), Material Master, Stock Transfer SAP SD: Sales Order, Delivery, Picking & Goods Issue, Billing, Credit Management, Pricing, Returns Integration: MM-SD, SD-FI, MM-FI document flow and data consistency
Out of Scope | SAP FI/CO standalone transactions, SAP HR module, Performance testing, Security/Authorization testing
Testing Types | Functional Testing ¦ Integration Testing ¦ Regression Testing ¦ UAT ¦ End-to-End (E2E) Testing ¦ Negative Testing
3. Test Objectives
Primary Objectives | 1. Verify core business processes in SAP MM and SD function per business requirements 2. Validate data integrity across system interfaces (MM↔SD, SD↔FI) 3. Confirm end-to-end O2C and P2P cycles execute without errors 4. Identify and document defects before production release 5. Provide test sign-off for go-live approval
4. Test Environment
System | SAP ECC 6.0 – Quality Assurance (QA) Client
SAP Client | 800 (QA) ¦ 100 (Dev) ¦ 200 (UAT)
Transport Path | DEV (100) → QA (800) → UAT (200) → PRD (300)
Test Tools | JIRA (defect tracking & test management) ¦ MS Excel (test cases & reports) ¦ SAP GUI 7.40
Access Required | SAP QA client login ¦ ME51N, ME21N, MIGO, MIRO, VA01, VL01N, VF01 T-codes
5. Test Schedule & Milestones
Phase | Activity | Start Date | End Date | Owner
Phase 1 | Test Planning & Review | 01-Mar-2023 | 03-Mar-2023 | Eluru Priyanka
Phase 2 | Test Case Design (MM) | 04-Mar-2023 | 08-Mar-2023 | Eluru Priyanka
Phase 3 | Test Case Design (SD) | 08-Mar-2023 | 12-Mar-2023 | Eluru Priyanka
Phase 4 | Test Execution – Functional | 13-Mar-2023 | 22-Mar-2023 | Eluru Priyanka
Phase 5 | Integration & E2E Testing | 23-Mar-2023 | 27-Mar-2023 | Eluru Priyanka
Phase 6 | Defect Fixing & Retest | 28-Mar-2023 | 05-Apr-2023 | Dev + QA
Phase 7 | UAT | 06-Apr-2023 | 12-Apr-2023 | Business Users + QA
Phase 8 | Test Sign-Off & Closure | 13-Apr-2023 | 14-Apr-2023 | QA Lead
6. Entry & Exit Criteria
Entry Criteria | • Test environment (SAP QA client) is available and stable • All transports from Dev are moved to QA client • Master data (material, vendor, customer) configured in QA • Test cases reviewed and approved • JIRA project created and team has access
Exit Criteria | • All high and critical test cases executed • No open Critical or High severity defects • Test execution rate ≥ 95% • Pass rate ≥ 90% for all test cases • Test summary report signed off by QA Lead and Business
7. Risk & Mitigation
Risk | Severity | Probability | Mitigation
QA environment instability | High | Medium | Engage SAP Basis team for daily health checks; backup client available
Incomplete master data in QA | Medium | High | Data preparation checklist verified before test execution starts
Resource unavailability | Medium | Low | Cross-training team member as backup; test cases documented in detail
Scope creep mid-cycle | High | Medium | Change control process; any new scope requires QA Lead approval
8. Defect Management Process
Tool | JIRA – all defects logged, tracked, and closed in JIRA
Severity Levels | Critical ¦ High ¦ Medium ¦ Low
Defect Workflow | New → Assigned → In Progress → Fixed → Retest → Closed / Reopen
SLA – Critical | Fix within 1 business day; retest same day
SLA – High | Fix within 2 business days
SLA – Medium | Fix within 5 business days
9. Test Deliverables
Deliverables | 1. Test Plan (this document) 2. SAP MM Test Cases (Excel) 3. SAP SD Test Cases (Excel) 4. Defect Log with status tracker (JIRA + Excel) 5. SQL Data Validation Queries 6. Test Execution Summary Report 7. UAT Sign-Off Document
10. Sign-Off
Role | Name | Signature | Date | Status
QA Engineer | Eluru Priyanka | [Signed] | 14-Apr-2023 | Approved
Functional Lead | [Functional Lead Name] | [Signed] | 14-Apr-2023 | Approved
Business Owner | [Business Owner Name] | [Signed] | 14-Apr-2023 | Approved